## Checklist
sequence | content | assignee_email | start_date | end_date | estimated_hours | status
1 | [Foundation/completed] Established the Vue 3 + Vite application shell, AppShell, layouts, sidebar/header, theme controls, route metadata, and catch-all route in new_webui/frontend/src/App.vue, src/app/layouts, and src/app/router.ts. | dedenh842@gmail.com |  |  | 0 | completed
2 | [Navigation/completed] Established the current Web UI navigation model with Dashboard, Robot, Maps, Mission, Station, Zone, and Alarm destinations plus Robot Detail, Map Edit, Map Survey, and Mission Edit subroutes in new_webui/frontend/src/app/navigation.ts and src/app/router.ts. | dedenh842@gmail.com |  |  | 0 | completed
3 | [Shared foundation/completed] Established environment configuration, REST client, Pinia stores, domain types, reusable controls, tables, cards, dialogs, skeletons, status badges, empty states, and confirmation patterns in new_webui/frontend/src/app, src/shared, src/domain, and src/stores. | dedenh842@gmail.com |  |  | 0 | completed
4 | [Backend foundation/completed] Established the FastAPI + SQLite application factory, migrations, request-scoped database access, health/readiness endpoints, settings, map storage configuration, and CORS handling in new_webui/backend/app. | dedenh842@gmail.com |  |  | 0 | completed
5 | [Backend resources/completed] Implemented persistence and REST endpoints for robots, desired mode, maps/files, stations, zones, missions, and mission runs with schemas, repositories, validation, and backend tests in new_webui/backend/app and new_webui/backend/tests. | dedenh842@gmail.com |  |  | 0 | completed
6 | [Verification/in_progress] Run and record the current baseline for new_webui/backend pytest, new_webui/frontend typecheck, frontend unit tests, and production build; separate existing failures from feature work and keep the source tree free of test-generated changes. | dedenh842@gmail.com | 2026-09-30 | 2026-10-01 | 6 | in_progress
7 | [Backend/frontend contract] Verify and close contract gaps between frontend API modules and FastAPI schemas for camelCase/snake_case mapping, PATCH omission versus null, conflict responses, map-file errors, robot-busy mission errors, readiness failures, and consistent user-facing error payloads in new_webui/frontend/src/shared/api and new_webui/backend/tests. | dedenh842@gmail.com | 2026-10-02 | 2026-10-06 | 14 | not_started
8 | [ROS bridge/completed] Implemented the browser ROS integration catalog and client foundation for topics, services, actions, reconnect/backoff, cached publishers, service calls, transient topics, TF, status vocabulary, topic health, and staleness in new_webui/frontend/src/domain/ros and src/app/ros. | dedenh842@gmail.com |  |  | 0 | completed
9 | [Robot registry/completed] Implemented robot CRUD, per-robot bridge URLs, fleet connection pooling, focused robot selection, vitals/full subscription tiers, robot detail routing, telemetry projection, topic-health display, and map/pose canvas foundations in new_webui/frontend/src/features/robot, src/stores/fleet.ts, src/stores/links.ts, and src/app/ros/pool.ts. | dedenh842@gmail.com |  |  | 0 | completed
10 | [Robot registry/runtime] Verify robot create/edit/delete, duplicate handling, robot switching, focused subscription teardown/restart, rosbridge reconnect/backoff, topic silence/staleness, stale telemetry clearing, and backend-unreachable states using RobotView.vue, RobotDetailView.vue, pool.ts, client.ts, and the new backend. | dedenh842@gmail.com | 2026-10-07 | 2026-10-12 | 16 | not_started
11 | [Dashboard/operate] Complete and verify DashboardView.vue, RobotDetailView.vue, links.ts, status.ts, and shared indicators so connectivity, agent state, mode, battery, dock state, telemetry freshness, activity, and command availability are consistent; disconnected, starting, stopping, and stale states must visibly block unsafe controls. | dedenh842@gmail.com | 2026-10-13 | 2026-10-16 | 16 | not_started
12 | [Navigation] Complete the Web UI set-pose and go-to-pose flow in RobotDetailView.vue and RobotMapCanvas.vue: require map/TF readiness, apply the command gate, show publish/action success or refusal, support cancellation/timeout/error feedback, and recover when /initialpose, /goal_pose, or the selected ROS interface is unavailable. Do not modify Nav2 internals. | dedenh842@gmail.com | 2026-10-19 | 2026-10-22 | 16 | in_progress
13 | [Teleoperation/E-stop] Complete and verify DriveJoystick.vue, useGamepad.ts, domain/teleop.ts, SurveyView.vue, and EmergencyStop.vue so manual control publishes only /teleop/cmd_vel, deadman/focus rules are visible, zero commands are sent on stop/unmount/watchdog expiry, browser disconnect removes command authority, and physical E-stop is explicitly authoritative. | dedenh842@gmail.com | 2026-10-23 | 2026-10-27 | 18 | in_progress
14 | [Mapping/survey] Verify SurveyView.vue end to end: request map mode through /robot_mode, establish teleoperation, display map/scan/pose/SLAM status, stop safely, invoke /map_save, refresh the backend map registry, and recover clearly from agent refusal, missing telemetry, map-save failure, backend failure, or rosbridge loss. | dedenh842@gmail.com | 2026-10-28 | 2026-11-02 | 22 | in_progress
15 | [Mapping/telemetry] Verify LiveMapCanvas.vue, useRobotTelemetry.ts, SlamIndicator.vue, TF fallback behavior, scan/costmap/plan rendering, rendering performance, stale-data indicators, and cleanup when the focused robot changes or the survey route is left. | dedenh842@gmail.com | 2026-11-03 | 2026-11-05 | 14 | not_started
16 | [Maps/registry] Verify MapsView.vue and map API/store behavior for upload, YAML/image download, validation, rename, replace-image, archive/delete, version/hash display, map-in-use errors, empty/loading/error states, and robot map assignment/switching against new_webui/backend/app/api/maps.py and robots.py. | dedenh842@gmail.com | 2026-11-06 | 2026-11-11 | 20 | in_progress
17 | [Maps/editor] Complete and verify MapEditorView.vue, MapEditCanvas.vue, useMapEditor.ts, and domain/map/edit.ts for map rendering, cell edits, undo/redo, save/publish, reload/version behavior, invalid map handling, and destructive confirmation; keep edited map data consistent with backend map versions. | dedenh842@gmail.com | 2026-11-12 | 2026-11-17 | 20 | not_started
18 | [Stations] Verify StationView.vue, StationMapCanvas.vue, stationType.ts, stations.ts, and backend station APIs for create/edit/delete, map scoping, station type validation, pose editing, teach-from-robot, duplicate/error handling, empty/loading states, and synchronization of persisted stations to the robot-side Web UI contract. | dedenh842@gmail.com | 2026-11-18 | 2026-11-20 | 16 | in_progress
19 | [Zones] Verify ZoneView.vue, ZoneMapCanvas.vue, zoneKind.ts, zones.ts, and backend zone APIs for drawing/editing/deletion, polygon validation, keepout/avoid/speed/binary settings, map scoping, persistence, visible refresh, and delivery to /amr/zones; document and test the startup/QoS dependency without changing unrelated navigation implementation. | dedenh842@gmail.com | 2026-11-23 | 2026-11-26 | 18 | in_progress
20 | [Mission authoring] Complete MissionView.vue and MissionEditorView.vue for mission create/edit/delete, map selection, ordered station steps, task type, continue/manual-confirm behavior, duplicate/invalid station validation, draft persistence, destructive confirmation, and all loading/empty/error states. | dedenh842@gmail.com | 2026-11-27 | 2026-12-03 | 22 | in_progress
21 | [Mission execution] Verify the mission run lifecycle from frontend to backend to the existing robot-side contract: start validation, robot selection, live polling, progress/step/lap state, stop-after-lap, cancel, failure, agent restart recovery, completed history, and clear recovery actions in missions.ts, MissionView.vue, and backend mission/run APIs. | dedenh842@gmail.com | 2026-12-04 | 2026-12-10 | 24 | in_progress
22 | [Mission contract] Resolve the Web UI-visible task semantics mismatch between frontend values, backend stored steps, robot_agent mapping, and custom_interfaces/action/MissionPlan.action; define one documented enum mapping and add contract tests. Limit ROS work to the interface contract required by the Web UI. | dedenh842@gmail.com | 2026-12-11 | 2026-12-14 | 10 | not_started
23 | [Docking UI] Implement the missing docking feature inside the new Web UI: station selection, dock/undock/cancel controls, confirmation, dock state/progress feedback, timeout/error/retry states, unsafe-state disabling, and integration through the existing /dock_command and /dock_status contract. Do not implement or redesign the docking algorithm. | dedenh842@gmail.com | 2026-12-15 | 2026-12-21 | 24 | not_started
24 | [Alarm UI/completed] Implemented the AlarmView.vue presentation, active versus acknowledged sections, severity mapping, timestamps, acknowledge-one, acknowledge-all, and the alarms Pinia store foundation. | dedenh842@gmail.com |  |  | 0 | completed
25 | [Alarm integration] Connect alarms.ts and AlarmView.vue to actual Web UI-relevant sources: rosbridge disconnects, stale critical telemetry, backend failures, command refusals, mission/docking failures, and robot status faults; preserve acknowledgement/history behavior and prevent duplicate alarm storms. | dedenh842@gmail.com | 2026-12-22 | 2026-12-28 | 20 | not_started
26 | [UX feedback] Standardize loading, empty, disconnected, stale, permission-denied, validation, timeout, retry, and recovery feedback across dashboard, robot, navigation, teleoperation, survey, maps, stations, zones, missions, docking, and alarms using the existing shared components and toast/confirmation patterns. | dedenh842@gmail.com | 2026-12-29 | 2027-01-04 | 18 | not_started
27 | [Backend reliability] Add focused backend tests and hardening for map-file atomicity, missing-file behavior, map assignment constraints, one-live-run-per-robot enforcement, mission progress reporting, station/zone deletion constraints, migration/readiness failures, and stable HTTP error payloads consumed by the frontend. | dedenh842@gmail.com | 2027-01-05 | 2027-01-08 | 20 | not_started
28 | [Security/access] Define and implement the new Web UI access boundary: protect backend robot/configuration endpoints, return actionable 401/403 states to the frontend, and ensure the deployment contract does not expose unauthenticated robot-control paths through the new UI or its rosbridge connection. | dedenh842@gmail.com | 2027-01-11 | 2027-01-15 | 22 | not_started
29 | [Runtime packaging] Provide a standalone new_webui runtime package and operator documentation covering backend startup, frontend production build, environment variables, health/readiness checks, map/database paths, per-robot rosbridge registration, and the explicit relationship to the still-existing legacy UI. | dedenh842@gmail.com | 2027-01-18 | 2027-01-20 | 14 | not_started
30 | [Legacy boundary] Remove accidental new_webui dependence on legacy API defaults and stale documentation, and document the explicit cutover boundary so new_webui cannot silently fall back to the root backend/web-ui when configuration is missing. | dedenh842@gmail.com | 2027-01-21 | 2027-01-22 | 10 | not_started
31 | [Feature verification] Execute feature-level acceptance for navigation, robot context, dashboard, telemetry, teleoperation/E-stop, mapping, map management, stations, zones, missions, docking UI, alarms, reconnects, and failure recovery against a running new backend and rosbridge-connected ROS environment; record evidence per feature. | dedenh842@gmail.com | 2027-01-25 | 2027-01-29 | 30 | not_started
32 | [Final release] Review the final new_webui source, tests, runtime documentation, API/ROS contracts, safety states, feature evidence, and legacy boundary; confirm no checklist item requires Gazebo, URDF, sensor simulation, Nav2/SLAM internals, docking algorithm, physical robot implementation, or unrelated ros2_ws development. | dedenh842@gmail.com | 2027-02-01 | 2027-02-02 | 8 | not_started